## Semua Modul
No | Platform | Modul | Bobot | Start Date | End Date | Hari Kerja | Catatan
1 | WEB | [WEB] - Data Master - Master Produk | 2 | 2026-07-22 | 2026-07-27 | 4 | CRUD + LOV API SKU, hitung harga jual dari pajak
2 | WEB | [WEB] - Data Master - Pelanggan - Master Pelanggan | 2 | 2026-07-28 | 2026-07-31 | 4 | CRUD multi field (alamat, channel, status)
3 | WEB | [WEB] - Data Master - Pelanggan - Channel | 1 | 2026-08-03 | 2026-08-04 | 2 | CRUD sederhana
4 | WEB | [WEB] - Data Master - Master Pegawai | 1 | 2026-08-05 | 2026-08-06 | 2 | CRUD sedang, field terbatas
5 | WEB | [WEB] - Data Master - Pajak | 1 | 2026-08-07 | 2026-08-10 | 2 | CRUD sederhana + validasi referensi
6 | WEB | [WEB] - Data Master - Lainnya - Alasan | 1 | 2026-08-11 | 2026-08-12 | 2 | CRUD sederhana (enum tipe)
7 | WEB | [WEB] - Data Master - Lainnya - Stokis / Grosir | 2 | 2026-08-13 | 2026-08-19 | 4 | CRUD + detail stok per produk / history
8 | WEB | [WEB] - Penjualan - Faktur | 5 | 2026-08-20 | 2026-09-02 | 9 | Transaksi lengkap: item, diskon, pajak, status, cetak
9 | WEB | [WEB] - Penjualan - Stok Motoris | 3 | 2026-09-11 | 2026-09-16 | 4 | Monitoring agregat stok per salesman
10 | WEB | [WEB] - Kunjungan - Informasi Kunjungan | 3 | 2026-09-17 | 2026-09-22 | 4 | List/filter laporan kunjungan
11 | WEB | [WEB] - Kunjungan - Geografis Kunjungan | 3 | 2026-09-23 | 2026-09-30 | 6 | Peta + aggregasi metrik sales per wilayah
12 | MOBILE | [MOBILE] - Beranda | 1 | 2026-08-10 | 2026-08-12 | 3 | KPI harian, sync accordion, grid menu entry
13 | MOBILE | [MOBILE] - Dasbor | 1 | 2026-08-13 | 2026-08-18 | 3 | Filter periode, chart, agregasi performa
14 | MOBILE | [MOBILE] - Profil | 1 | 2026-08-19 | 2026-08-19 | 1 | Info user + logout
15 | MOBILE | [MOBILE] - Target KPI | 1 | 2026-08-20 | 2026-08-20 | 1 | Progress target kunjungan & rupiah
16 | MOBILE | [MOBILE] - Kunjungan - Rute Kunjungan | 1 | 2026-08-21 | 2026-08-26 | 3 | List rute harian, filter status, FAB
17 | MOBILE | [MOBILE] - Kunjungan - Detail Kunjungan | 3 | 2026-08-27 | 2026-09-02 | 5 | GPS check-in, stokis, multi aktivitas visit
18 | MOBILE | [MOBILE] - Penjualan - Faktur Penjualan | 1 | 2026-09-03 | 2026-09-07 | 3 | Daftar faktur + filter + navigasi detail
19 | MOBILE | [MOBILE] - Penjualan - Sales Order (dalam Visit) | 2 | 2026-09-08 | 2026-09-11 | 4 | Katalog qty UOM, hitung total dalam konteks visit
20 | MOBILE | [MOBILE] - Penjualan - Input Transaksi Mandiri | 1 | 2026-09-14 | 2026-09-16 | 3 | Faktur langsung offline di luar alur visit
21 | MOBILE | [MOBILE] - Penjualan - Detail Faktur | 1 | 2026-09-17 | 2026-09-17 | 1 | Read-only detail + aksi cetak sederhana
22 | MOBILE | [MOBILE] - Penagihan AR - Daftar Piutang | 1 | 2026-09-18 | 2026-09-18 | 1 | List outstanding AR + filter status
23 | MOBILE | [MOBILE] - Penagihan AR - Input Pembayaran | 1 | 2026-09-21 | 2026-09-23 | 3 | Multi-invoice, metode bayar, bukti transfer
24 | MOBILE | [MOBILE] - Outlet & Produk - Cek Stok / Belanja Stokis | 1 | 2026-09-24 | 2026-09-28 | 3 | Cek stok kanvas + alur kulakan
25 | MOBILE | [MOBILE] - Outlet & Produk - Katalog Produk | 1 | 2026-09-29 | 2026-09-29 | 1 | Grid katalog + search/filter
26 | MOBILE | [MOBILE] - Outlet & Produk - Detail Produk | 1 | 2026-09-30 | 2026-09-30 | 1 | Read-only harga/stok/promo
27 | MOBILE | [MOBILE] - Outlet & Produk - Review Kulakan | 1 | 2026-10-01 | 2026-10-01 | 1 | Review konfirmasi restock stokis
28 | MOBILE | [MOBILE] - Outlet & Produk - Geo Tag / Daftar Outlet | 2 | 2026-10-02 | 2026-10-06 | 3 | List outlet + status GPS
29 | MOBILE | [MOBILE] - Outlet & Produk - Detail Outlet | 2 | 2026-10-07 | 2026-10-09 | 3 | Profil + peta + update lokasi
30 | MOBILE | [MOBILE] - Outlet & Produk - Tambah Outlet | 2 | 2026-10-12 | 2026-10-14 | 3 | Form registrasi + foto + geotag
31 | MOBILE | [MOBILE] - Sinkronisasi - Antrean Upload | 1 | 2026-10-15 | 2026-10-19 | 3 | Queue offline, retry, status sync
32 | MOBILE | [MOBILE] - FALCON MERGER - Visit Plan | 3 | 2026-10-20 | 2026-11-05 | 13 | Merger modul Visit Plan ke Falcon Mobile (rute + detail visit)
33 | MOBILE | [MOBILE] - FALCON MERGER - POA | 3 | 2026-11-06 | 2026-11-24 | 13 | Merger modul POA ke Falcon Mobile
34 | MOBILE | [MOBILE] - FALCON MERGER - Partner | 2 | 2026-11-25 | 2026-12-07 | 9 | Merger modul Partner / outlet ke Falcon Mobile
35 | MOBILE | [MOBILE] - FALCON MERGER - Dashboard | 2 | 2026-12-08 | 2026-12-17 | 8 | Merger Dashboard / KPI ke Falcon Mobile
|  | TOTAL | 60 | 2026-07-22 | 2026-11-30 | 135 | Timeline WEB & MOBILE paralel ¦ excl. weekend + libur nasional RI ¦ 22 Jul – 30 Nov 2026 ¦ v3: −Canvassing +4 FALCON MERGER

## Timeline WEB
No | Platform | Modul | Bobot | Start Date | End Date | Hari Kerja | Catatan
1 | WEB | [WEB] - Data Master - Master Produk | 2 | 2026-07-22 | 2026-07-27 | 4 | CRUD + LOV API SKU, hitung harga jual dari pajak
2 | WEB | [WEB] - Data Master - Pelanggan - Master Pelanggan | 2 | 2026-07-28 | 2026-07-31 | 4 | CRUD multi field (alamat, channel, status)
3 | WEB | [WEB] - Data Master - Pelanggan - Channel | 1 | 2026-08-03 | 2026-08-04 | 2 | CRUD sederhana
4 | WEB | [WEB] - Data Master - Master Pegawai | 1 | 2026-08-05 | 2026-08-06 | 2 | CRUD sedang, field terbatas
5 | WEB | [WEB] - Data Master - Pajak | 1 | 2026-08-07 | 2026-08-10 | 2 | CRUD sederhana + validasi referensi
6 | WEB | [WEB] - Data Master - Lainnya - Alasan | 1 | 2026-08-11 | 2026-08-12 | 2 | CRUD sederhana (enum tipe)
7 | WEB | [WEB] - Data Master - Lainnya - Stokis / Grosir | 2 | 2026-08-13 | 2026-08-19 | 4 | CRUD + detail stok per produk / history
8 | WEB | [WEB] - Penjualan - Faktur | 5 | 2026-08-20 | 2026-09-02 | 9 | Transaksi lengkap: item, diskon, pajak, status, cetak
9 | WEB | [WEB] - Penjualan - Stok Motoris | 3 | 2026-09-11 | 2026-09-16 | 4 | Monitoring agregat stok per salesman
10 | WEB | [WEB] - Kunjungan - Informasi Kunjungan | 3 | 2026-09-17 | 2026-09-22 | 4 | List/filter laporan kunjungan
11 | WEB | [WEB] - Kunjungan - Geografis Kunjungan | 3 | 2026-09-23 | 2026-09-30 | 6 | Peta + aggregasi metrik sales per wilayah
|  | TOTAL | 24 | 2026-07-22 | 2026-09-30 | 43 | Timeline WEB ¦ excl. weekend + libur nasional RI ¦ 22 Jul – 30 Sept 2026 ¦ v3: Canvassing take-out

## Timeline MOBILE
No | Platform | Modul | Bobot | Start Date | End Date | Hari Kerja | Catatan
1 | MOBILE | [MOBILE] - Beranda | 1 | 2026-08-10 | 2026-08-12 | 3 | KPI harian, sync accordion, grid menu entry
2 | MOBILE | [MOBILE] - Dasbor | 1 | 2026-08-13 | 2026-08-18 | 3 | Filter periode, chart, agregasi performa
3 | MOBILE | [MOBILE] - Profil | 1 | 2026-08-19 | 2026-08-19 | 1 | Info user + logout
4 | MOBILE | [MOBILE] - Target KPI | 1 | 2026-08-20 | 2026-08-20 | 1 | Progress target kunjungan & rupiah
5 | MOBILE | [MOBILE] - Kunjungan - Rute Kunjungan | 1 | 2026-08-21 | 2026-08-26 | 3 | List rute harian, filter status, FAB
6 | MOBILE | [MOBILE] - Kunjungan - Detail Kunjungan | 3 | 2026-08-27 | 2026-09-02 | 5 | GPS check-in, stokis, multi aktivitas visit
7 | MOBILE | [MOBILE] - Penjualan - Faktur Penjualan | 1 | 2026-09-03 | 2026-09-07 | 3 | Daftar faktur + filter + navigasi detail
8 | MOBILE | [MOBILE] - Penjualan - Sales Order (dalam Visit) | 2 | 2026-09-08 | 2026-09-11 | 4 | Katalog qty UOM, hitung total dalam konteks visit
9 | MOBILE | [MOBILE] - Penjualan - Input Transaksi Mandiri | 1 | 2026-09-14 | 2026-09-16 | 3 | Faktur langsung offline di luar alur visit
10 | MOBILE | [MOBILE] - Penjualan - Detail Faktur | 1 | 2026-09-17 | 2026-09-17 | 1 | Read-only detail + aksi cetak sederhana
11 | MOBILE | [MOBILE] - Penagihan AR - Daftar Piutang | 1 | 2026-09-18 | 2026-09-18 | 1 | List outstanding AR + filter status
12 | MOBILE | [MOBILE] - Penagihan AR - Input Pembayaran | 1 | 2026-09-21 | 2026-09-23 | 3 | Multi-invoice, metode bayar, bukti transfer
13 | MOBILE | [MOBILE] - Outlet & Produk - Cek Stok / Belanja Stokis | 1 | 2026-09-24 | 2026-09-28 | 3 | Cek stok kanvas + alur kulakan
14 | MOBILE | [MOBILE] - Outlet & Produk - Katalog Produk | 1 | 2026-09-29 | 2026-09-29 | 1 | Grid katalog + search/filter
15 | MOBILE | [MOBILE] - Outlet & Produk - Detail Produk | 1 | 2026-09-30 | 2026-09-30 | 1 | Read-only harga/stok/promo
16 | MOBILE | [MOBILE] - Outlet & Produk - Review Kulakan | 1 | 2026-10-01 | 2026-10-01 | 1 | Review konfirmasi restock stokis
17 | MOBILE | [MOBILE] - Outlet & Produk - Geo Tag / Daftar Outlet | 2 | 2026-10-02 | 2026-10-06 | 3 | List outlet + status GPS
18 | MOBILE | [MOBILE] - Outlet & Produk - Detail Outlet | 2 | 2026-10-07 | 2026-10-09 | 3 | Profil + peta + update lokasi
19 | MOBILE | [MOBILE] - Outlet & Produk - Tambah Outlet | 2 | 2026-10-12 | 2026-10-14 | 3 | Form registrasi + foto + geotag
20 | MOBILE | [MOBILE] - Sinkronisasi - Antrean Upload | 1 | 2026-10-15 | 2026-10-19 | 3 | Queue offline, retry, status sync
21 | MOBILE | [MOBILE] - FALCON MERGER - Visit Plan | 3 | 2026-10-20 | 2026-11-05 | 13 | Merger modul Visit Plan ke Falcon Mobile (rute + detail visit)
22 | MOBILE | [MOBILE] - FALCON MERGER - POA | 3 | 2026-11-06 | 2026-11-24 | 13 | Merger modul POA ke Falcon Mobile
23 | MOBILE | [MOBILE] - FALCON MERGER - Partner | 2 | 2026-11-25 | 2026-12-07 | 9 | Merger modul Partner / outlet ke Falcon Mobile
24 | MOBILE | [MOBILE] - FALCON MERGER - Dashboard | 2 | 2026-12-08 | 2026-12-17 | 8 | Merger Dashboard / KPI ke Falcon Mobile
|  | TOTAL | 36 | 2026-08-10 | 2026-12-17 | 92 | Timeline MOBILE ¦ excl. weekend + libur nasional RI ¦ 10 Agu 2026 – 17 Des 2026 ¦ v3: reschedule start 2026-08-10 (+4 FALCON MERGER)

## Ringkasan
Ringkasan Timeline & Bobot (v3)
WEB dan MOBILE paralel (dev berbeda). WEB: 22 Jul – 30 Sep 2026. MOBILE: 10 Agu 2026 – 17 Des 2026. Hari kerja = Senin–Jumat dikurangi libur nasional/cuti bersama RI (SKB 3 Menteri 2026). v3: hapus Canvassing (take-out); +4 FALCON MERGER; Mobile di-reschedule mulai 10 Agu 2026.
Platform | Jumlah Modul | Total Bobot | Start Date | End Date | Hari Kerja
WEB | 11 | 24 | 2026-07-22 | 2026-09-30 | 43
MOBILE | 24 | 36 | 2026-08-10 | 2026-12-17 | 92
TOTAL | 35 | 60 | 2026-07-22 | 2026-12-17 | 43 + 92 (2 track)
Libur yang dikecualikan (dalam periode)
Tanggal | Hari | Keterangan | Sumber
2026-08-17 | Senin | Libur Nasional — Proklamasi Kemerdekaan RI | SKB 3 Menteri 2026
2026-08-25 | Selasa | Libur Nasional — Maulid Nabi Muhammad SAW | SKB 3 Menteri 2026
Catatan: Juli, September, Oktober & November 2026 tidak ada libur nasional/cuti bersama menurut SKB (selain Aug). Hanya weekend yang dikecualikan di bulan tersebut.
Aturan alokasi tanggal
1. Durasi modul proporsional terhadap bobot di track-nya (WEB / MOBILE).
2. Tanggal berurutan atas→bawah per track.
3. Hanya hari kerja efektif: Senin–Jumat, minus libur nasional & cuti bersama RI.
4. Track WEB: 22-Jul-2026 s/d 30-Sep-2026 (Canvassing dihapus di v3). Track MOBILE: 10 Agu 2026 s/d 17 Des 2026 (reschedule 2026-08-10; + FALCON MERGER setelah Sinkronisasi).
5. Skala bobot: 1 ringan – 5 sangat berat. Target total bobot = 60 (WEB 24 + MOBILE 36). FALCON MERGER: Visit Plan 3, POA 3, Partner 2, Dashboard 2.
6. Warna kuning = sudah berjalan (jangan diubah). Merah = take-out (dihapus di v3). Bobot Mobile existing disesuaikan di v3 agar total tetap 60.